## Project summary
Project Name: | DfT Street Manager
Content links | Introduction
Guidance and navigation
Dashboard
Issues
Risks
Assumptions
Dependencies
Decisions

## Introduction
Purpose of this document
The risks, issues, actions and decisions log (RAID log) allows you to capture, prioritise, assess and manage these to ensure appropriate levels of governance to support transition. This allows you to manage all inter-dependencies that might impact the success of transition, as well as define and review the effectiveness of mitigation tactics.
Best practice
It is advisable that you manage this as a live document and update it on a weekly basis to keep track of progress and take any actions if necessary.
Typical considerations (please note this is not an exhaustive list)
Group | Consideration
Internal stakeholders | Internal stakeholders - support and sign-off required
Internal stakeholders | Internal stakeholders - readiness to move to Street Manager
External stakeholders | External stakeholders relationship management
External stakeholders | Co-ordination of transition to Street Manager with key LHAs/ Utilities / Contractors
External stakeholders | Relationship management and collaboration with software vendors
System dependencies | Level of uncertainty regarding system fit
System dependencies | System readiness - build, test and implement
System dependencies | Interdependencies with other systems (e.g. Street Manager and asset management systems)
Processes | Inrterdepencies between processes
Processes | Risk of disruption to BAU
Business performance | Impact on user journey
Business performance | Impact on business outcomes
Business performance | Budget, resource or capacity constraints
Business performance | Time constraints

## Guidance and navigation
RAID Log
Definitions
Risk: | An uncertain event or set of events, that should it occur, will have an effect on the achievement of the Programme / Project objecives
Assumption: | A statement that is taken as being true for the purpose of planning, but which could change later.
Issue: | Either guaranteed to occur or has already occured and action is required to address and overcome its impact.
Dependency: | An output from one task or another project is needed as a mandatory input for another task or another project.
Mitigation: | The activity that has been identified to prevent a risk from materialising (or minimise it's impact). Mitigations should be assigned to an operational owner who is responsible for ensuring that mitigating activities are undertaken.
Impact: | The assessment of what will happen if a risk materialises, or what is happening because of an issue. This should be quantified in terms of time / cost / quality.
Probability: | The evaluated likelihood of a particular threat or opportunity actually happening.
Risk Score - Probability and Impact
IMPACT | Severe | 5 | 5 | 10 | 15 | 20 | 25
| Major | 4 | 4 | 8 | 12 | 16 | 20
| Moderate | 3 | 3 | 6 | 9 | 12 | 15
| Minor | 2 | 2 | 4 | 6 | 8 | 10
| Minimal | 1 | 1 | 2 | 3 | 4 | 5
| PROBABILITY |  | 1 | 2 | 3 | 4 | 5
Risk RAG Status
Red | Major concern - Executive Steering Group intervention is required for immediate action
Amber | Minor concern - Mitigation actions / Decisions required from the Steering Group. Issues identified but under control
Green | Normal level of attention - Risk or Issue is being actively managed without potential threat to delivery
Complete | No risk remaining - Risk has either been mitigated or has disappeared (Or has become an issue and moved to Issues Log)
Impact Levels
1 | Minimal | Little or no impact on achieing outcome objectives, schedule and budget not affected.
2 | Minor | One or more stated outcome objectives will fall below goals but well above minimum acceptable levels, minor effect on budget and schedule (within tolerances).
3 | Moderate | One or more stated outcome objectives will fall goals but above minimum acceptable levels, moderate schedule slip and impact on budget.
4 | Major | One or more stated outcome objectives wil fall below acceptable levels, increases critical path and budget is highly impacted. Project Partially Deliverable, full delivery requires Project re-plan.
5 | Severe | One or more critical outcome objectives will not be achieved, L0 milestone / event delayed and budget is severely impacted. Project undeliverable within schedule.
Probability Levels
1 | Very Low | Very unlikely
2 | Low | Unlikely
3 | Medium | Possible
4 | High | Probable
5 | Very High | Almost certain
Issue Impact Analysis and Impact Levels
1 | Low | Inconvenient - Consequences fine although limited remedial action required
2 | Medium | Manageable within plan - Minor variation to schedule (could need re-planning) but for limited scope of activities only
3 | High | Replan or delay the project - New approach needed to ensure delivery of project. Likely impact at team level
4 | Critical | Replan programme or delay to multiple projects - Impact on delivery of workstream or significant (>5%) effect on schedule, budget, functionality, or quality
5 | Severe | Goal threatening - Could impact ability to deliver programme or lead to unacceptable delays, cost over-runs or scope/quality reductions
Field Definitions
Field | Mandatory | Field Description
ID | Yes | Used to assign a unique identifier to the RAID. Ensure that the owners adhere to a standard naming convention. This may vary depending on the client
Workstream | No | Used to identify which workstream the risk, issue and dependency is associated to
Title | Yes | RAID items should have a title assigned to them and should be a very short description of the item. This is particularly helpful for reporting purposes
Description | Yes | Used to descrie the RAID item. Naming conventions for Risks and issues should be followed.
Raised By | Yes | Individual that raised the item in the first instance i.e. originator
Risk To | Yes | Used to identify what is impacted by the risk i.e Benefit, Cost, Deliverable, Resource, Schedule
Status | Yes | Used to identify the status of the RAID items - Open, In Progress, Escalated, On Hold, Closed
Risk Mitigation | Yes | Used to explain action to mitigate the risks
Comments | No | Any related comment to a particular RAID item. Every comment should have a date against it for audit purposes.
Owner | Yes | The name of the individual that is responsible for any action, resolution or mitigation being completed by the target date
Date Raised | Yes | Date when RAID item was raised
Mitigation Due Date | Yes | Date the Mitigating action is due
Mitigation Completion Date | Yes | Date the mitigating action(s) was / were completed
Date Closed | Yes | Date the RAID item was closed i.e. when the status was changed to closed. In some cases this may be the same as the mitigation completion date
Escalation Level | Yes | Used to outline what level of escalation is required
Corresponding Milestone ID | No | Used to assign the correspnding milestone I.D. to a dependency
Dependency Type | Yes | Used to describe the type of dependency i.e. is it an inbound or outbound dependency
Dependency Category | Yes | Used to describe what category the dependency falls under. Is it internal to the project or external? Please Note: The definition wil vary depending on the type of project
Planned Delivery Date | Yes | Original delivery date of the RAID item
Forecast Delivery Date | Yes | Forecasted delivery date of the RAID item. This is only used when the planned Delivery date has been missed
Reciever | Yes | The team, department or individual receiving the dependency, aslo known as depender
Impact if not delivered | Yes | Used to descrie the impact if the RAID Item is not delivered
Proposed Action / Resolution | Yes | Used to describe the action (s) to resolve / resolution plan of the RAID item
Date Last Reviewed | Yes | The date a particular item was last reviewed. This can aso be the date it was updated.
Expected Close date | Yes | Date RAID item was expected to be closed. This is different from planned delivery date because it focuses on closure of the item
Reason | Yes | Used to describe the justification behind an assumption
Assumption Status | Yes | Used to descrbe whether an assumption has been validated or not. Assumptions that have been validated should have also been accepted by the relevant approver
Impact if Assumption is incorrect | Yes | Used to describe the impact on the project if the assumption prove to be incorrect
Meeting Raised | No | Used to describe any meetings raised against an action or decision item
Actionee / Approver | Yes | Used to describe th eindividual responsible for performing an action or approving a decision
Associated RAID ID | No | Used to assign the associated risk, assumption, issue or dependency to an action or decision item
Level on Plan | Yes | Used to show the level of the dependency on the plan

## Dashboard
Risks |  | Assumptions |  | Issues |  | Dependencies
0 |  | 0 |  | 0 |  | 0
0 | Open | 0 | Open | 0 | Open | 0 | Open
0 | In Progress | 0 | In Progress | 0 | In Progress | 0 | In Progress
0 | Closed | 0 | Closed | 0 | Escalated | 0 | Closed
|  |  |  | 0 | Closed
0 | 1 - Minimal | 0 | 1 - Low | 0 | 1 - Low | 0 | 1 - Low
0 | 2 - Minor | 0 | 2 - Medium | 0 | 2 - Medium | 0 | 2 - Medium
0 | 3 - Moderate | 0 | 3 - High | 0 | 3 - High | 0 | 3 - High
0 | 4 - Major | 0 | 4 - Critical | 0 | 4 - Critical | 0 | 4 - Critical
0 | 5 - Severe |  |  | 0 | 5 - Severe

## Issues
ID | Related Risk ID | Area | Portfolio | Status (Open, In Progress, Escalated, Closed) | Workstream | Issue Description (1.Event, 2. Cause, 3.Impact) (THERE IS AN ISSUE THAT ... DUE TO... WHICH HAS RESULTED IN...) | Impact (1-5) | Actions and Update | Owner | Raised By | Identified date | Title (Brief Summary of Issue) | Last update date | Actionee | Due Date | lessons learned | Escalated Level | Date Last Reviewed
I001
I002
I003
I004
I005
I006

## Risks
ID | Title (Brief Summary of Risk) | Risk Level | Status (Open, Closed) | Risk Response | Workstream | Risk overview | Risk Description (1.Event, 2. Cause, 3. Impact) (THERE IS A RISK THAT... BECAUSE.... WHICH MAY LEAD TO...) | Risk To | Impact (1=Minimal - 5=Severe) | Probability (1=Low - 5=High) | RAG | Mitigation plan and status | Owner | Date Raised | Raised by | Last update / review | Due Date | Comments (Date - Comments) | Mitigation Completion Date | Date Closed | Escalation Level
R001 | Need clarity of vendor selection process | [9 empty] | 0
R002 | POC content / product to be confirmed | [9 empty] | 0
R003 | Progamme management | [9 empty] | 0
R004 | Data | [9 empty] | 0
R005 | Organisational transformation | [9 empty] | 0
R006 | Customer impact | [9 empty] | 0
R007 | Availabiltiy of product team resources | [9 empty] | 0
R008 | [10 empty] | 0
R009 | [10 empty] | 0
R010 | [10 empty] | 0
R011 | [10 empty] | 0
R012 | [10 empty] | 0
R013 | [10 empty] | 0
R014 | [10 empty] | 0
R015 | [10 empty] | 0
R016 | [10 empty] | 0
R017 | [10 empty] | 0
R018 | [10 empty] | 0
R019 | [10 empty] | 0
R020 | [10 empty] | 0
R021 | [10 empty] | 0
R022 | [10 empty] | 0
R023 | [10 empty] | 0
R024 | [10 empty] | 0
R025 | [10 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Assumptions
ID | Area | Workstream | Title (Brief summary of the Assumption) | Assumption Description | Impact | Raised By | Date Identified | Assumption Actions | Last Updated | New Review Date | Owner | Status (Open, In Progress, Closed) | Reason (Justification) | Assumption Status (Validated, Invalidated) | Rank (Critical, High, Medium, Low) | Date Closed
A002
A003
A004
A005
A006
A007
A008
A009
A010
A011
A012
A013

## Dependencies
ID | Workstream Impacted | Interdependency Title | Dependent on Workstream | Dependency Description | Planned Actions to Manage Dependency | Action Due | RAG | Owner | Status (Open, Closed) | Impact of failure to manage | Raised by | Date Identified | Last Update | Risk Reference | Dependency Type (Inbound, Outbound) | Dependency Category (Internal, External) | Planned Delivery Date | Forecast Delivery Date | Receiver | Priority (C, H,M,L) | Comments (Date - Comments) | Level on Plan
D001
D002
D003

## Decisions
ID | Type (Action - Decision) | Date raised | Description | Priority | Owner | Actionee / Approver | Panned Delivery Date | Forecasted Delivery Date | Progress / Comments (Date - Comments) | Status (Open, In Progress, On Hold, Closed) | Date Closed | Associated RAID ID
DN001
DN002
DN003
DN004
DN005
DN006
DN007
DN008
DN009
DN010
DN011
DN012
DN013