## 1. Project Summary
Project Name: | DfT Street Manager
Content links | 2. Guidance notes
3. Dashboard
4. Engagement and training needs assessment
5. Engagement and training tracker
Pivots

## 2. Guidance notes
Why use an engagement and training tracker?
This tracker allows you to methodically assess the engagement / communication and training needs of all your stakeholders - both internal and external. It helps you track what type and intensity of engagement and training is needed and by when. It also tracks progress against each activity as well as how effective the intervention has been in achieving the desired outcome and so that you can take any needed actions (e.g. if your objective is to make someone who is resistant (a blocker) suppotive (a champion) and have engaged with them via 1-2-1 comms, but they are still negative (ie outcome is not achieved) you might want to consider engaging them via leadership (e.g. their manager). You can also use the dashboards for a quick view of needed effort and progress - please note that you have to complete the information abiding by the formatting rules listed below to make sure the formulas driving the dashboards are working!
Guidance and questions to consider when filling in the NEEDS ASSESSMENT
* Yellow cells contain formulas | Examples have been provided to show you how to add information in the tool and demonstrate the functionality of the dashboard - PLEASE OVERWRITE THEM WITH YOUR REAL DATA!
Area | Information to fill in | Good to have in mind
Stakeholder information: Stakeholder; Internal / External ; Team ; Role | Include factual information - you can either do it at a group level (e.g. by team) or at individual level. Make sure that you include ALL INTERNAL AND EXTERNAL stakeholders (e.g. users, IT staff, management, external IT vendors, other LHAs/Utilities/Contractors that you work with, DfT and any other regulatory bodies, etc.) | Include everyone that will have a role in your organisation's transition to Street Manager
Stakeholder information: Baseline scenario | Using the stakeholder analysis matrix techniques (see the Change management pack for reference) allocate each stakeholder to 1) Champion (Influential and positive), 2) Adopter (Less influential but positive), 3) Observer (Neutral), 4) Opposer (Less influential but negative), 5) Blocker (Influential and negative) | You are free to choose another classification as long as it works for you and allows you to establish the current grouping of your stakeholders as a baseline | Link to Chance management strategy
Stakeholder information: Target scenario | Using the same or similar classification, note down what your target state is for each stakeholder | Be ambitious, but realistic - you might not be able to convert all Blockers into Champions!
Engagement needs assessment: Amount of engagement needed | Fill in "Low' / "Medium"/ "High" for each row | It is likely that as a minimum Champions and Blockers might need 'High' level of engagement.
Engagement needs assessment: Target date | Enter the date by which you want to engage each stakeholder | Please, do enter a date for each row, as this will impact the live dashboards. If not sure, enter your best estimate
Engagement needs assessment: Type of engagement activity | Enter 'Yes' for each activity that should be put in place | This is not an exhaustive list of activities - feel free to add (by copy/pasting) or amend activity descriptions as needed. Consider all channels and techniques (see the 'Comms approach' for reference) and think of what is feasible and what are the preferences of your stakeholders | Link to Comms approach
Training needs assessment: What training is needed | Are the stakeholders going to use Street Manager website? Will they need training on new processes and workflows? | Regardless of whether you will be transitioning via the website or linking via API there might be changes in the way processes are delivered - which might call for training on the new ways of working
Training needs assessment: Target date | Enter the date by which you want to train each stakeholder | Please, do enter a date for each row, as this will impact the live dashboards. If not sure, enter your best estimate
Training needs assessment: Type of engagement activity | Has the new technology been developed and made available? | This is not an exhaustive list of activities - feel free to add (by copy/pasting) or amend activity descriptions as needed. Consider all channels and techniques (see the 'Training approach' for reference) and think of what is feasible and what are the preferences of your stakeholders | Link to Training approach
Guidance and questions to consider when filling in the TRACKER
* Yellow cells contain formulas | Examples have been provided to show you how to add information in the tool and demonstrate the functionality of the dashboard - PLEASE OVERWRITE THEM WITH YOUR REAL DATA!
Area | Information to fill in | Good to have in mind
Stakeholder information: Stakeholder; Internal / External ; Team ; Role | NO NEED TO FILL IN - THE INFORMATION WILL FLOW IN FROM THE NEEDS ASSESSMENT VIA FORMULA | n/a
Stakeholder information: Baseline scenario | NO NEED TO FILL IN - THE INFORMATION WILL FLOW IN FROM THE NEEDS ASSESSMENT VIA FORMULA | n/a
Stakeholder information: Target scenario | NO NEED TO FILL IN - THE INFORMATION WILL FLOW IN FROM THE NEEDS ASSESSMENT VIA FORMULA | n/a
Engagement needs assessment: Target date | NO NEED TO FILL IN - THE INFORMATION WILL FLOW IN FROM THE NEEDS ASSESSMENT VIA FORMULA | n/a
Training needs assessment: Target date | NO NEED TO FILL IN - THE INFORMATION WILL FLOW IN FROM THE NEEDS ASSESSMENT VIA FORMULA | n/a
Activities status | Mark the complete ones 'Complete' | Make sure that you only use the word 'Complete' as this drives the live dashboards!
Progress | NO NEED TO FILL IN - A FORMULA CALCULATES THE OVERALL PERCENTAGE PULLING INFORMATION FROM THE NEEDS ASSESSMENT SHEET AND THE TRACKER ('COMPLETE') SECTION
Outcome | Has the objective (Target scenario) been achieved? | This is not linked to dashboards, but included for your reference
Stakeholder Mapping: Reference
Classification | Characteristics | Engagement approach
Champion: High Influence - Supportive | Influencial and supporting the project, which mean they can be an advocate to help influence and bring on board other stakeholders | Priority stakeholders - Build close relationship to turn them into allies, create opportunity to use them as advocates or change champions within their communities
Adopter: Low Influence - Supportive | Supportive but has got less influence over other stakeholders | Engage with them sooner rather than later to keep them supportive, try to empower them to become champions
Observer: High/Low Influence - Neutral | Neither positive nor negative prevails, which means they might be undecided in their attitude and behaviour | Monitor them (especially if high power), try to engage to make them supportive (e.g. via champions)
Opposer: Low Influence - Resistant | Negative towards the project, however not powerful enough to influence others | Bring them into supportive environment (e.g. champion community), monitor for potential increase of their power
Blocker: High Influence - Resistant | Negative towards the project and powerful enough to influence others (e.g. opposers and observers), which might build up overall level of resistance | Priority stakeholders - Engage and support them to reduce resistance / move them towards neutral or supportive. Monitor their engagement with and influence over other stakeholders

## 3. Dashboard
4362200%
Total numbers of stakeholders to be engaged
0
Progress so far
77.78%
Total numbers of stakeholders to be trained
0
Progress so far
70%

## 4. Engagement and training need
STAKEHOLDER INFORMATION | [5 empty] | ENGAGEMENT NEEDS ASSESSMENT | [5 empty] | TRAINING NEEDS ASSESSMENT
Stakeholder details |  |  |  | Baseline scenario | Target scenario | Amount of engagement needed | When do they need to be engaged by? | Which of the following engagement interventions need to be implemented to support this stakeholder? Select "Yes" if it must be put in place |  |  |  | Will they be using Street Manager? | Is Street Manager system training needed? | Is process / workflow training needed? | When do they need to be trained by? | Which of the following training interventions need to be implemented to support this stakeholder? Select "Yes" if it must be put in place
Stakeholder | Internal / external | Team / Department | Role | Champion / Adopter/ Observer / Opposer / Blocker | Champion / Adopter / Observer | Low / Medium / High | Enter date / n/a | Targeted 1-2-1 communications | Group comms and engagement (e.g. via communities) | Less frequent online communication | Leadership engagement | Yes / No | Yes / No | Yes / No | Enter date / n/a | Online / video click guide | F2F training | Drop-in session | Peer training | Training on process changes
Stakeholder 1 | External | External | External role | Champion | Champion | High | 2019-06-01 | Yes |  |  | Yes | No | No | No | n/a
Stakeholder 2 | Internal | Team 1 | Role 2 | Champion | Champion | High | 2019-06-01 | Yes |  |  | Yes | Yes | Yes | Yes | 2019-09-19 | Yes | Yes |  |  | Yes
Stakeholder 3 | Internal | Team 1 | Role 3 | Adopter | Adopter | Medium | 2019-06-01 |  | Yes |  |  | Yes | Yes | Yes | 2019-09-19 | Yes |  | Yes |  | Yes
Stakeholder 4 | Internal | Team 1 | Role 3 | Blocker | Observer | High | 2019-07-01 | Yes |  | Yes |  | No | No | Yes | 2019-11-19 | Yes | Yes |  | Yes | Yes
Stakeholder 5 | Internal | Team 2 | Role 1 | Opposer | Observer | Medium | 2019-09-01 |  | Yes | Yes |  | Yes | Yes | Yes | 2019-09-19 | Yes |  |  |  | Yes
Stakeholder 6 | Internal | Team 2 | Role 2 | Opposer | Observer | Medium | 2019-09-01 |  | Yes | Yes |  | No | No | No | 2019-11-19 | Yes | Yes | Yes | Yes
Stakeholder 7 | Internal | Team 3 | Role 1 | Blocker | Observer | High | 2019-07-01 | Yes |  |  | Yes | No | No | Yes | 2019-11-19 |  |  | Yes |  | Yes
Stakeholder 8 | Internal | Team 3 | Role 3 | Champion | Champion | High | 2019-06-01 | Yes | Yes |  |  | Yes | Yes | Yes | 2019-09-19 | Yes |  |  |  | Yes
Stakeholder 9 | Internal | Team 3 | Role 3 | Adopter | Champion | High | 2019-06-01 | Yes | Yes |  |  | No | No | Yes | 2019-11-19 |  |  |  |  | Yes
Stakeholder 10 | External | External | External role | Observer | Adopter | Medium | 2019-08-01 |  | Yes | Yes |  | No | No | No | n/a
Stakeholder 11 | Internal | Team 4 | Role 2 | Observer | Adopter | Medium | 2019-08-01 |  | Yes | Yes |  | Yes | Yes | Yes | 2019-09-19 | Yes | Yes |  |  | Yes
Stakeholder 12 | Internal | Team 4 | Role 2 | Blocker | Observer | High | 2019-07-01 | Yes | Yes |  | Yes | Yes | Yes | Yes | 2019-09-19 | Yes |  | Yes |  | Yes

## 5. Engagement and training trac
These fields are prepopulated with formulas to mirror the needs assessment sheet!
Stakeholder details |  |  |  | Baseline scenario | Target scenario | When do they need to be engaged by? | When do they need to be trained by? | Progress so far: Engagement Enter 'Complete' if activity has been completed | [5 empty] | Progress so far: Training Enter 'Complete' if activity has been completed
Stakeholder | Internal / External | Team / Department | Role | Champion / Adopter/ Observer / Opposer / Blocker | Champion / Adopter / Observer | Engagement Date / N/A | Training Date / N/A | Targeted 1-2-1 communications | Group comms and engagement (e.g. via communities) | Less frequent online communication | Leadership engagement | Progress (CONTAINS FORMULA) | Outcome (has the target been achieved or is more engagement needed) | Online / video click guide | F2F training | Drop-in session | Peer training | Training on process changes | Progress | Outcome (has the target been achieved or is more engagement needed)
Stakeholder 1 | External | External | External role | Champion | Champion | 2019-06-01 | n/a | Complete |  |  | Complete | 100% |  | Complete
Stakeholder 2 | Internal | Team 1 | Role 2 | Champion | Champion | 2019-06-01 | 2019-09-19 |  |  | Complete | Complete | 100% | [5 empty] | Complete | 33.33%
Stakeholder 3 | Internal | Team 1 | Role 3 | Adopter | Adopter | 2019-06-01 | 2019-09-19 |  | Complete |  |  | 100% |  |  | Complete | Complete |  |  | 66.67%
Stakeholder 4 | Internal | Team 1 | Role 3 | Blocker | Observer | 2019-07-01 | 2019-11-19 | Complete |  | Complete | Complete | 150% | [6 empty] | 0%
Stakeholder 5 | Internal | Team 2 | Role 1 | Opposer | Observer | 2019-09-01 | 2019-09-19 | Complete |  |  |  | 50% |  | Complete |  | Complete |  | Complete | 150%
Stakeholder 6 | Internal | Team 2 | Role 2 | Opposer | Observer | 2019-09-01 | 2019-11-19 |  | Complete |  | Complete | 100% | [6 empty] | 0%
Stakeholder 7 | Internal | Team 3 | Role 1 | Blocker | Observer | 2019-07-01 | 2019-11-19 | Complete |  |  |  | 50% |  |  |  | Complete | Complete |  | 100%
Stakeholder 8 | Internal | Team 3 | Role 3 | Champion | Champion | 2019-06-01 | 2019-09-19 |  |  | Complete | Complete | 100% |  | Complete |  |  |  |  | 50%
Stakeholder 9 | Internal | Team 3 | Role 3 | Adopter | Champion | 2019-06-01 | 2019-11-19 |  |  |  |  | 0% |  |  |  | Complete |  | Complete | 200%
Stakeholder 10 | External | External | External role | Observer | Adopter | 2019-08-01 | n/a |  | Complete |  |  | 50% | [5 empty] | Complete
Stakeholder 11 | Internal | Team 4 | Role 2 | Observer | Adopter | 2019-08-01 | 2019-09-19 |  | Complete |  | Complete | 100% |  |  | Complete |  |  |  | 33.33%
Stakeholder 12 | Internal | Team 4 | Role 2 | Blocker | Observer | 2019-07-01 | 2019-09-19 |  |  |  | Complete | 33.33% |  |  |  | Complete | Complete |  | 66.67%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Pivots
Stakeholder | (Multiple Items)
Engagement needs | Team / Department
Target date to engage by | External | Team 1 | Team 2 | Team 3 | Team 4 | Grand Total
2019-06-01 | 1 | 2 |  | 2 |  | 5
2019-07-01 |  | 1 |  | 1 | 1 | 3
2019-08-01 | 1 |  |  |  | 1 | 2
2019-09-01 |  |  | 2 |  |  | 2
Grand Total | 2 | 3 | 2 | 3 | 2 | 12
Stakeholder | (Multiple Items)
Engagement progress | Engagement Date / N/A
Team / Department | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | Grand Total
External | 100% |  | 50% |  | 75%
Team 1 | 100% | 150% |  |  | 116.7%
Team 2 |  |  |  | 75% | 75%
Team 3 | 50% | 50% |  |  | 50%
Team 4 |  | 33.33% | 100% |  | 66.67%
Grand Total | 80% | 77.78% | 75% | 75% | 77.78%
Stakeholder | (Multiple Items)
Internal / external | (Multiple Items)
Training needs | Team / Department
Target date to train by | Team 1 | Team 2 | Team 3 | Team 4 | Grand Total
2019-09-19 | 2 | 1 | 1 | 2 | 6
2019-11-19 | 1 | 1 | 2 |  | 4
Grand Total | 3 | 2 | 3 | 2 | 10
Stakeholder | (Multiple Items)
Internal / External | Internal
Training progress | Training Date / N/A
Team / Department | 2019-09-19 | 2019-11-19 | Grand Total
Team 1 | 50% | 0% | 33.33%
Team 2 | 150% | 0% | 75%
Team 3 | 50% | 150% | 116.7%
Team 4 | 50% |  | 50%
Grand Total | 66.67% | 75% | 70%