## 1. Project summary
Project Name: | DfT Street Manager
Content links | 2. Guidance and best practice
3. Readiness Dashboard
4. People readiness
5. Processes readiness
6. Tech readiness
7. Pivots

## 2. Guidance and best practice
Why should I do a Change Readiness Assessment
A change readiness assessment will allow you to understand in greater detail how ready each part of your organisation is to undergo the transition over to Street Manager. From your completed assessement you will have a holistic view of the readiness of your entire organisation, broken down into people, processes and technology. This will help to form the basis of your change approach, delivery plan and where more attention is required.
When should I do a Change Readiness Assessment
A readiness assessment is usually performed at the beginning of any project to aid planning, however it is a good practice to treat this as a live document and monitor any movements so that the plan can be kept relevant and updated if needed. It is also advisable to repeat the overall assessment at a later stage to ensure that it takes into account any updates in available information, e.g.: one department, which was the focus of early efforts, is now ready to transition. You will also benefit from performing a final readiness assessment as a checkpoint prior to go-live to ensure that the organisation is ready to go (or assess any risks if the assessment shows otherwise).
How do I do a Change Readiness Assessment
1) This tool consists of a People readiness sheet, Processes readiness sheet, Technology readiness sheet, and a Readiness Dashboard that summarises these three sheets. 2) You should break your readiness assessment down into people, processes and technology using the template sheets provided for each of these. 3) When considering the impact on People, you may wish to consider whether the team/department will have to change their processes or systems as a result of the change and add these to the Processes and Technology sheets. 4) When considering the impact on Processes and Technology, make sure that you add the relevant teams/departments, because the summary dashboard is organised by team/department. If there are no specific teams associated with the entry, please enter 'ALL' 5) The templates are set up so that by entering "yes" or "no" to the readiness assesment questions, the readiness percentage will automatically update. This will also align to an overall % readiness that will appear on the Readiness Dashboard, alongside overall readiness for people, processes and technology. These will automatically update and so you do not need to edit them. 6) Examples have been provided for each of the three templates - please overwrite them with your content.
Questions to consider when doing a Change Readiness Assessment
Organisation area | Questions to consider | Possible implications and considerations
People - population size | How many people are currently working on permit/noticing systems? | Current population affected - implications for communications, awareness and expectations management as well as effort required
People - population size | How many people will be using Street Manager? | Stakeholder engagement and buy-in
People - population size | If number is different, what is the reason for this? | Potentially people coming on to Street Manager who have not previously used Eton - readiness will possibly be lower
People - roles and responsibilities | Would there be any change of roles and responsibilities? | Possible need for negotiation of contracts and job descriptions and upskilling
People - organisation structure | Would there be any change in organisation structures? | Organisation re-design, redeployment of staff and possible consultation
People - organisation structure | Would there be any change in reporting lines? | Communications and possible contract re-negotiation
People - culture and behaviour | Would there be a need for shift in culture or ways of working? | Communications and possible contract re-negotiation (e.g. if ways of working are changing)
Processes - number of processes affected | How many business processes will be affected by the change? | Link to related business outcomes and teams involved in delivery: What measures do we need to have in place and who needs to be involved to ensure successful delivery?
Processes - number of processes affected | Would there be any new processes required to deliver outcomes? | Link to roles and responsibilities, staff capacity and user journey: How do we make sure that user journey is not impacted negatively?
Processes - number of processes affected | Would any of the existing processes cease to exist? | Link to roles and responsibilities, staff capacity and user journey: How do we minimse disruption to BAU?
Processes - complexity of processes | How complex are the impacted processes? | Time required to transition, business change required to support to-be process adoption, risks of BAU disruption
Processes - complexity of processes | How many handoffs and interdependencies exist between affected processes? | Approach to transitioning to new processes (e.g. big bang or phased), risks of BAU disruption
Processes - complexity of processes | What other dependencies and linkages to other processes do need to be considered? | Approach to transitioning to new processes (e.g. big bang or phased), risks of BAU disruption
Technology - adoption approach | Is API the preferred adoption method to use Street Manager? | Lead time and investment required to develop API, lower level of change in user experience, no need for extensive system training
Technology - adoption approach | Is UI/Web app the preferred adoption method to use Street Manager? | Higher level of change in user experience and requirement for training on new UI
Technology - IT environment | How complex is the current IT environment when it comes to permit/noticing systems? | Gap analysis and transition planning to assess what can be replaced when, review of contractual agreements with software vendors
Technology - IT environment | Are current permit/noticing systems integrated to other software - e.g. asset management? | Engagement and collaboration with service providers of those systems, planning for and delivery of system integration work (e.g. via API)
Technology - IT environment | How many external IT systems (other LHAs/Utilities/contractors) would SM need to interact with? | Implications for length of duration of dual-running period, joint planning for transition
Technology - IT environment | Would there be a need for dual-running with current permit/noticing systems even after all linked external organisations have transitioned to Street Manager? | Resource requirements, review of workflows and quality assurance to minimise risk of any work falling through the gaps
Technology - IT capability | Is software mainly been developed and serviced internally or outsourced? | Time and capability required to build API / deliver system integration
Technology - IT capability | What are the organisation's relations with software vendors? | Level of flexibility to renegotiate contracts, source new vendors, cost of IT
Links and dependencies | What is the priority organisational element that will be considered when it comes to designing the desired future state? | Benefits and KPIs definition, acceptable trade-offs between benefits and investment required to achieve them
Links and dependencies | How does this align to organisaitonal strategy? | Benefits and KPIs definition, acceptable trade-offs between benefits and investment required to achieve them
People - Engagement | Have people been engaged? | The earlier and more frequently people are engaged, the more ready they are likely to be
People - Engagement | Do they understand their future role? | If they do not understand, they are unlikely to be ready as they will not have been able to accurately plan for the future
People - Engagement | Do they need to be trained? | They will not be fully ready to transition until training has been complete and therefore readiness and training approaches will be linked
People - Engagement | Have they already been trained? | They will not be fully ready to transition until training has been complete and therefore readiness and training approaches will be linked
People - Engagement | Do they feel confident to settle into the future state? | Confidence will be linked to how ready they feel and thus how ready they are
Processes - Future | Have you designed your future processes? | Future processes will need to be in place in order to work out how ready your organisation is to transition over to them
Processes - Future | Have they been signed off? | Processes will need to be signed off by the appropriate level
Processes - Future | Do you know the dependencies? | Before understanding how ready your processes are to change over, you need to consider what dependencies exist so that they can be taken into account and planned for prior to transition
Processes - Future | Do you have a mitigation plan for any disruptions? | The period between beginning and completing transition has the potential for some disruption, particularly in terms of processes. In order to ensure readiness for the change, a mitigation plan to minimise these disruptions is essential especially when considering user and customer journey and business outcomes.
Processes - Future | Are the processes ready to be launched? | Have the future processes been tested and validated? Do they meet the acceptance criteria in terms of business outcomes?Have they been given an owner and is it clear who will be responsible to deliver and maintain them?
Technology - Future | Has all IT been developed? | Consider all the various forms of IT and how they will interact with each other
Technology - Future | Has all IT been tested? | Testing will highlight any potential disruptions or weak spots prior to transition
Technology - Future | Have all dependencies been assessed? | IT dependencies may include adjusting the API prior to transition etc.
Technology - Future | Are there measures in place to avoid disruption to BAU? | As part of the wider mitigation plan, potential IT disruptions should be planned for
Technology - Future | Is all IT ready for roll out? | All new software/APIs will need to be tested and ready for launch in line with transition.

## 4. People readiness
People - details | [6 empty] | Change - details |  | Readiness assessment |  |  |  |  | 63.33%
Stakeholder | Department/Team (enter 'ALL' if there is no specific team/dept associated) | Current users of permit / notice systems (Y/N) | Expected user of Street Manager (Y/N) | Region | Urban / local / both | Details of permits used | Current state Summary | Future state Summary (e.g. API / UI, other change factors) | Have they been engaged? | Do they understand the change and how it will impact them | Do they need training | Have they received training | Are they confident they can settle in the future state? | Overall readiness | * *Yellow cells contain formulas
John Smith 1 | PIPE | Y | Y | London | Urban |  | EToN | SM UI | Yes | Yes | Yes | Yes | Yes | 100%
John Smith 2 | PIPE | Y | Y | London | Urban |  |  |  | Yes | No | Yes | No | Yes | 60%
John Smith 3 | Water | Y | Y | London | Urban |  |  |  | Yes | Yes | No | Yes | No | 60%
John Smith 4 | Water | Y | Y | London | Urban |  |  |  | Yes | Yes | Yes | Yes | Yes | 100%
John Smith 5 | PIPE | Y | Y | London | Urban |  |  |  | No | No | No | No | No | 0%
John Smith 6 | PIPE | Y | Y | London | Urban |  |  |  | Yes | No | No | Yes | Yes | 60%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## 5. Processes readiness
Process - details |  |  | Change - details |  | Readiness assessment |  |  |  |  | 60%
Process | Department/Team (enter 'ALL' if there is no specific team/dept associated) | Link to business outcome | Current state Summary | Future state Summary | Has the future process been designed? | Has the future process been signed off? | Have all dependencies been assessed? | Are there measures in place to avoid disruption to BAU | Is the future process ready for implementation | Overall readiness | * *Yellow cells contain formulas
Permits | PIPE |  | EToN | Street Manager | Yes | No | Yes | Yes | No | 60%
Section 85 | Water |  | EToN | Street Manager | Yes | No | No | No | No | 20%
Section 58 | Gas |  | EToN | Street Manager | Yes | Yes | Yes | Yes | Yes | 100%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## 6. Tech readiness
Technology - details |  |  | Change - details |  | Readiness assessment |  |  |  |  | 60%
System | Department/Team (enter 'ALL' if there is no specific team/dept associated) | Link to other systems | Current state Summary | Future state Summary | Has all IT been developed? | Has all IT been tested? | Have all dependencies been assessed? | Are there measures in place to avoid disruption to BAU | Is all IT ready for roll out? | Overall readiness | * *Yellow cells contain formulas
System 1 | PIPE |  |  |  | Yes | No | Yes | Yes | No | 60%
System 2 | PIPE |  |  |  | Yes | Yes | Yes | Yes | Yes | 100%
System 3 | Water |  |  |  | Yes | No | No | No | No | 20%
System 4 | Water |  |  |  | Yes | Yes | Yes | No | No | 60%
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!
#DIV/0!

## 7. Pivots
PEOPLE READINESS |  | PROCESS READINESS |  | TECHNOLOGY READINESS
Stakeholder | (Multiple Items) | Process | (Multiple Items) | System | (Multiple Items)
Row Labels | Average of Overall readiness | Department/Team (enter 'ALL' if there is no specific team/dept associated) | PROCESS | Department/Team (enter 'ALL' if there is no specific team/dept associated) | TECH
Water | 0.5 | Gas | 1 | PIPE | 0.8
PIPE | 0.4 | PIPE | 0.6 | Water | 0.4
Grand Total | 0.43333 | Water | 0.2 | Grand Total | 0.6
|  | Grand Total | 0.6
SUMMARY OF ORGANISATION READINESS
People | 63.33%
Processes | 60%
Technology | 60%
Overall | 61.11%